## Product Backlog
Product Backlog | [9 empty] | Priority Key | Story Points Key
Project: |  | 3821ICT Mental Health Care AI Chatbot | [7 empty] | 1 - mandatory; High | 1 - Very Easy
Team: |  | HopeChat Devs | [7 empty] | 2 - mandatory; Medium | 2 - Easy
[10 empty] | 3 - mandatory; Low | 3 - Medium
Identifier | Theme | As a/an | I want to | so that | Notes | Priority | Story Points | Sprint Assigned | Status |  | 4 - Complexe
5 - Extremly Complexe
U1 | Portablity | user | download the application through Google App Store (Google Play Store) | search HopeChat in the GAS | the application is about a mental health care chatbot | 1 | 2 | 1 | In progress
|  | User | Allow the app to run on both computer and phone | more people can access HopeChat
U2 | Usability | user | choose the persona which I would like to chat with | I click the button on the specific smartphone screen or on pc's | the button could be larger for better user interaction | 2 | 5 | 1 | In progress
U3 |  | user | create an account in HopeChat | I can login the application using my account |  | 1 | 1 | 3 | In progress
U4 | Functionality | user | Mute the HopeChat | I do not need chat with it every second | the mute function should be defined by mutting time | 1 | 2 | 2 | In progress
U5 |  | user | have Hopechat set goals(daily reminders) | I can achieve a successful Therapy
U6 | Accessibility | user | use HopeChat via voice message | I can access the chatbot without typing |  | 2 | 4 | 1 | In progress
U7 |  | user | contact support team via email | I can submit the feedback |  | 1 | 3 | 1 | In progress
|  | user | be able to access Hopechat 24/7 | I can access Hopechat in times of need
U8 |  | user | have access to a HopeChat tutorial | I am shown what i can do with HopeChat and know whether or not it will fill my needs |  | 1 | 3 | 1 | in progress
U9 |  | Admin | make conversations private and secure | Hopechat can protect the privacy of its users |  | 2 | 7 | 2 | in progress
U10 |  | user | Make basic conversation with Hopechat | I can receive basic help with my mental health |  | 1 | 5 | 2 | in progress
U11 |  | user | Recieve links to addidional mental health services | I can receive addiational help beyond that of hopechat |  |  |  |  | in future
U12 |  | user | Access Hopechat through a webpage | I can access mental health support anywhere |  | 3 | 2 | 1 | in progress
U13 |  | user | Access hopechat in English | I can recieve mental health support in a language I speak |  | 1 | 1 | 2 | in progress
Note on B5: ====== ID#AAAAXmbWPi4 soeadmin (2022-04-14 01:24:35) Group your user stories into classes (categories): ie Access Management, Workflow, Scheduling, Admin etc - whatever is appropriate to your product

## Changes
Changes
Id | Theme | Issue and Solution | Notes | Status | Status | Description
C1 | Download | the user could not find app in GAS | set up GAS downliad link | TD | TD | to do
C2 | Access | the user could not access user profile | reset the permission to user | TD | IP | in progress
C3 | GUI | the user is unable to see chatbox | change the GUI settings | TD | IF | in future
C4 | Booking | the user could not book the physical meeting | rearrange the meeting | IF | D | done
C5 | AI model | Intergration between front-end and back-end | merge and make program talk to eachother | IP
C6 | AI model | GTP2 model using default dataset | use only Virtual Psychology dataset | IP
C7 | File | changes in proposal | proposal updates | D
C8 | Coding | AI model choice: GPT2/GPT3/GPT-Neo | GPT2 - better training | D
C9 | Meeting | on-site meeting for all members | Zoom meeting | D
C10 | Team Role | personal issues | temporary role change | D
C11 | AI model | data formatting issues | GPT2 | D

## Acceptance Criteria
Acceptance Criteria
Project: |  | 3821 ICT Mental Health Care AI Chatbot
Team: |  | HopeChat Devs
Identifier | Theme | User Story | Test Case | Test Progress | Notes | User Story
U1 | As a User | I can input text into the text box | TC1 | Tested by Mel | function in user interface | Done
U2 | As a User | I can click the send button to send text to the bot | TC2 | Tested by Mel | function in user interface | Done
U3 | As a User | I can view my sent message and the response from the bot on the screen | TC3 | Tested by Mel | function in user interface | Done
U4 | As a User | I can scroll up to see previous messages when the page reaches a certain limit | TC4 | Tested by Mel | function in user interface | Done
U5 | System | The back-end can receive data | TC5 | untested | waiting for model to be integrated | In progress
U6 | System | The trained model can process the data | TC6 | untested | waiting for model to be integrated | In progress
U7 | System | The back-end can output a response from the model | TC7 | untested | waiting for model to be integrated | In progress
[5 empty] | waiting for model to be integrated | In progress
U8 | System | The Model can detect 'flagged' words | TC8 | untested | waiting for model to be integrated | In progress
U9 | System | The model will send helpline links to the user if any flagged words are detected | TC9 | untested | waiting for model to be integrated | In progress
U10 | System | The model will save all users perivous session | TC10 | untested | waiting for model to be integrated | In progress
U11 | As a User | I can scoll up to see past conversations from a perivous session | TC11 | untested | waiting for model to be integrated | In progress
Note on B5: ====== ID#AAAAXmbWPi0 soeadmin (2022-04-14 01:24:35) Group your user stories into classes (categories): ie Access Management, Workflow, Scheduling, Admin etc - whatever is appropriate to your product