## Gantt
|  | Project Start Date: |  | 2022-03-14
|  | Project Name: 3821 ICT GC – Development a chatbot for ai-enable mental health support​ | [5 empty] | 2022
[7 empty] | week start from: | MAR | [17 empty] | APR | [29 empty] | MAY | [30 empty] | JUN
[8 empty] | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri
# | Tasks | Start Date | End Date | Duration | Status | % | Assign to | time axis 2022-03-14 to 2022-06-10
1 | Initiation - Project Team Formation | 2022-03-14 | 2022-03-20 | 5 | Complete | 1 | ALL | bar: 2022-03-14 to 2022-03-20
2 | Initiation - Initial team meeting | 2022-03-25 | 2022-03-25 | 1 | Complete | 3 | ALL | bar: 2022-03-25
3 | Initiation - Team Roles Identification | 2022-03-21 | 2022-03-27 | 5 | Complete | 6 | ALL | bar: 2022-03-21 to 2022-03-27
4 | Initiation - Initial Team Meeting With Assessor | 2022-03-29 | 2022-03-29 | 1 | Complete | 10 | BENNETT | bar: 2022-03-29; 2022-04-06; 2022-04-13; 2022-04-20; 2022-04-27; 2022-05-04; 2022-05-11; 2022-05-18; 2022-05-25; 2022-06-01
5 | Initiation - Initial Team Meeting With Clients | 2022-04-01 | 2022-04-01 | 1 | Complete | 15 | MELISSA | bar: 2022-04-01; 2022-04-12; 2022-04-19; 2022-04-26; 2022-05-03; 2022-05-10; 2022-05-17; 2022-05-24; 2022-05-31
6 | Initiation - Requirements Gathering | 2022-04-01 | 2022-04-05 | 3 | Complete | 18 | PEIDING | bar: 2022-04-01 to 2022-04-05
7 | Planning - Requirements Analyse | 2022-04-02 | 2022-04-08 | 5 | Complete | 22 | PEIDING | bar: 2022-04-02 to 2022-04-08
8 | Planning - Project Scope Definition | 2022-04-04 | 2022-04-04 | 1 | Complete | 25 | ALL | bar: 2022-04-04
9 | Planning - Skills set Identification | 2022-04-05 | 2022-04-12 | 6 | Complete | 28 | ALL | bar: 2022-04-05 to 2022-04-12
10 | Planning - Cost Analysis | 2022-04-16 | 2022-04-20 | 3 | Complete | 30 | PEIDING | bar: 2022-04-16 to 2022-04-20
11 | Planning - Project Proposal Approval | 2022-04-19 | 2022-04-19 | 1 | Complete | 35 | PEIDING | 2022-04-08: Extension
12 | Planning - Project Proposal Submission | 2022-04-22 | 2022-04-22 | 1 | Complete | 40 | BENNETT | bar: 2022-04-19
13 | Design - Requirements Refinement | 2022-04-08 | 2022-04-15 | 6 | Complete | 42 | ALL | bar: 2022-04-08 to 2022-04-15
14 | Design - Basic Graphic User Interface | 2022-04-19 | 2022-04-26 | 6 | Complete | 45 | MELISSA | bar: 2022-04-19 to 2022-04-26
15 | Design - Icon/Avatar | 2022-04-27 | 2022-05-03 | 5 | Complete | 50 | MELISSA | bar: 2022-04-27 to 2022-05-03
16 | Design - Dataset Lookup | 2022-04-27 | 2022-05-03 | 5 | Complete | 52 | DANIEL | bar: 2022-04-27 to 2022-05-03
17 | Design - AI model choosing | 2022-05-04 | 2022-05-10 | 5 | Complete | 54 | DANIEL | bar: 2022-05-04 to 2022-05-10
18 | Design - Further GUI Features | 2022-04-13 | 2022-04-19 | 5 | Complete | 60 | MELISSA
19 | Design - Chatbot Persona Design | 2022-04-14 | 2022-04-20 | 5 | In Progress | 62 | DANIEL
20 | Implementation - Basic GUI Coding | 2022-04-15 | 2022-04-21 | 5 | Complete | 66 | MELISSA | bar: 2022-04-19 to 2022-04-26
21 | Implementation - Dataset Dumping | 2022-04-16 | 2022-04-22 | 5 | Complete | 68 | DANIEL
22 | Implementation - AI Model Training | 2022-04-17 | 2022-04-23 | 5 | In Progress | 76 | DANIEL
23 | Implementation - Further GUI features | 2022-04-18 | 2022-04-24 | 5 | Complete | 80 | MELISSA
24 | Implementation - Persona | 2022-04-19 | 2022-04-25 | 5 | In Progress | 82 | DANIEL
25 | Implementation - Testing | 2022-04-20 | 2022-04-26 | 5 | Not Started | 85 | BENNETT
26 | Control - Project Management | 2022-03-14 | 2022-06-10 | 65 | Complete | 86 | PEIDING | bar: 2022-03-25; 2022-03-30; 2022-04-06; 2022-04-13; 2022-04-20; 2022-04-27; 2022-05-04; 2022-05-11; 2022-05-18; 2022-05-25; 2022-06-01
27 | Control - Risk Management | 2022-03-14 | 2022-06-10 | 65 | In Progress | 87 | LOUIE
28 | Control - Change Management | 2022-03-14 | 2022-06-10 | 65 | In Progress | 88 | BENNETT
29 | Control - Weekly Status Meeting | 2022-03-14 | 2022-06-10 | 65 | Complete | 90 | PEIDING | bar: 2022-03-30; 2022-04-06; 2022-04-13; 2022-04-20; 2022-04-27; 2022-05-04; 2022-05-11; 2022-05-18; 2022-05-25; 2022-06-01
30 | Control - Update Project Management Files | 2022-05-25 | 2022-06-10 | 13 | Complete | 92 | PEIDING | bar: 2022-03-25; 2022-03-31; 2022-04-07; 2022-04-14; 2022-04-21; 2022-04-28; 2022-05-05; 2022-05-12; 2022-05-19; 2022-05-26; 2022-06-02
31 | Closeout - Client Feedback | 2022-05-25 | 2022-05-25 | 1 | Complete | 95 | MELISSA | bar: 2022-05-25
32 | Closeout - Document Lesson Learned | 2022-05-25 | 2022-05-25 | 1 | Complete | 96 | PEIDING | bar: 2022-05-25
33 | Closeout - Update Files / Records | 2022-05-25 | 2022-06-01 | 6 | Complete | 98 | ALL | bar: 2022-05-25 to 2022-06-01
34 | Closeout - Final Deliverables Submission | 2022-06-03 | 2022-06-10 | 6 | In Progress | 100 | BENNETT | bar: 2022-06-03 to 2022-06-10
35 | Total | 2022-03-14 | 2022-06-10 | 65 |  | 100

## Data
Status
Not Started
In Progress
Stucked
Complete
Score
1
2
3
4
5
Risk Level
LOW
MEDIUM
HIGH
Name
BENNETT
DANIEL
LOUIE
MELISSA
PEIDING
ALL
NULL
Legends
Milestone
WMC
WMA
WSM
UPDATE
PM
EXT